## Sheet1
Date | Task | Issue
2015-07-29 | App. Team split into two groups to work on system requirements | N/A
| App. Team finished requirements lists. | N/A
| Requirements lists were combined into one list. | N/A
| App. team started collaborating for the UML design. | N/A
2015-08-03 | User story diagram | N/A
2015-08-05 | User story | N/A
| Classes discussion | N/A
| Use cases | N/A
| Core calculations | N/A
2015-08-10 | Developing the java objects | N/A
| Split team into making classes | N/A
| Nexus 9 emulator troubleshooting | N/A
| Core completion | N/A
| Main Application has been completed | N/A
2015-08-12 | Final JUnit testing | N/A
| Completing the remaining Javadocs. | N/A