## Sheet1
Number | Date Identified | Risk | Risk Category | Risk Probability | Risk Elimination Date | Risk Mitigation Plan | Comments
R-001 | 7/29/2015 | GitHub Integration - New users to Github, learning curve | Programmatic | 0.43 | 2015-08-12 | Provide a lead integration manager who is responisble for the GiHUb account and is knowledgeable in the GitHub commands and interface to provide support and answer questions about GitHub
R-002 | 7/29/2015 | Collaboration - New teams, figuring out each other strengths and weakness | Schedule | 0.43 | 2015-08-10 | People should collaborate with each other
R-003 | 7/29/2015 | No Shows - People not showing up for class period | Schedule | 0.33 | 2015-08-17 | Keep track of when people are not going to be in class due to scheduled circumstances. If there is an unforseen circum stance a person shall let thier leader know that they will not be in class so their part of the project can be delegated to other people.
R-004 | 7/29/2015 | lack of resources-some team members do not have android devices | Technical | 0.28 | 2015-08-17 | The emulator can be used in place of a physical device
R-005 | 7/29/2015 | Integration between UI and Java Code | Programmatic | 0.59 | 2015-08-12 | Constant contact between groups should be used
R-006 | 2015-08-03 | Different resources being used(GitHub, Google Docs, ect) | Programmatic | 0.41 | 2015-08-17 | If possible keep as much documents in one drive folder as possible
R-007 | 2015-08-05 | Project milestone not met, application not completed by 17th | Technical | 0.45 | 2015-08-17 | Teams will need to work together from home to complete application before the 17th
R-008 | 2015-08-10 | Team members in the groups are not communicating well with each other. Some team members feel that the team is disorganized | Schedule | 0.40 | 2015-08-10 | Team members plan to be more vocal about there needs. Team members plan to be more active into further assisting each other in the group.
R-009 | 2015-08-10 | Teams not utilizing GitHub to its full effect. | Programmatic | 0.34 | 2015-08-17 | People need to be pushing and syncing their code with GitHub whenever they have an update to the code. Instead of making two versions of each file, two branches should be made and then merged. | Syncing of code is needed to be able to revert back if needed. If you do not sync for a while and find out that a mistake was made there may be a chance of losing a lot of valuable code
R-010 | 2015-08-10 | Unable to get Nexus 9 emulator properly working | Technical | 0.36 | 2015-08-12 | Use team members phones
R-011 | 2015-08-10 | Teams not able to install Android SDK | Technical | 0.35 | 2015-08-10 | Team Members should ask for help from other teams and communicate more to solve the problem.