## Sheet1
Completion Date | Milestone Name | Team Assigned
7/29/2015 | System-Level Requirements | Java App & UI Teams
7/29/2015 | RMM & Data Dictionary documents started | LSI Team
2015-07-29 | Project Milestone Document | Project Manager
2015-08-03 | User Stories based off of SL Requirements | All Teams
2015-08-03 | RMM updated | LSI Team
2015-08-03 | Update Weekly Status Report | LSI Team
2015-08-05 | UML Modeling (AD, SD) | All Teams
2015-08-05 | Update Weekly Status Report | LSI Team
2015-08-10 | JUnit Test Classes | Java App & UI Teams
2015-08-10 | RMM Updated | LSI Team
2015-08-10 | Java classes completed | Java App & UI Teams
2015-08-10 | Update Weekly Status Report | LSI Team
2015-08-12 | Extra Credit Tasks | Java App & UI Teams
2015-08-12 | Java code to be integrated into Android | Integration Manager, App Team Lead, UI Team Lead
2015-08-12 | Java Application to be emulated into virtual device | Integration Manager
2015-08-12 | JavaDoc Completed | All Teams
2015-08-12 | RMM Completed with risk probability | LSI Team
2015-08-12 | Update Weekly Status Report | LSI Team
2015-08-17 | Demonstration of completed project to customer | LSI Team